## Project Details
OPTIONAL
Name of project:
Details: e.g. location
Details: e.g. dates etc
Details: e.g. team
SUMMARY OF THE PROJECT (what will be done, what are the key outputs and early outcomes:
[ insert project picture here]

## Project Model
OPTIONAL
Insert a picture of the Programme logic
It is helpful to insert a picture of the programme logic to make it easier for users to make sense of the monitoring sheet and its data, especially if they haven't looked at it before/for a while.

## Monitoring Sheet
Name of project
You could separate this out into more than one column if needed, e.g., separate out respsonsibility for collection, from analyse, from reporting.
Programme Logic | Box | QUESTION | HOW WOULD WE KNOW? | HOW WOULD WE MEASURE / EVIDENCE THIS? Is this a quantitative or qualitative measure? | Data collection SOURCE or MEASUREMENT METHOD | Interview questions | WHEN? Be specific of frequency if this needs to be collected routinely (e.g., monthly, quarterly, six-monthly, annually) | WHO? (Who is responsible to collect, analyse, report) | Assumptions | Projection/Target END OF YEAR/PROJECT | PROJECTION COMMENTARY | Baseline | Yr1 | Comments e.g. On track, off, track | Yr2 | Comments | Yr3 | Comments | ANYTHING ELSE?
[Input/activity/output/outcome] | [Copy the text inside the Programmel Logic box into here] | [What question might we ask to know this has happened/is happening?] | [Describe what would indicate this is happening - your indicator]. | [what would we need to measure of what kind of evidence would we need to be able to track the indicator] | [identify the information source(s) which will be used to gather data on the indicator] | [Insert the relevant interview questions (if applicable i.e., you have developed a standard set of interview questions to supplement data collection)] | [Insert time-frame (month and year) for when progress against this Indicator will be assessed - i.e. your monitoring visits] | [Insert name of person/people collecting this information] | [List any major assumptions related to this indicator or data collection method] | [Insert the target to be achieved by end of the project] | [Explain how project/target is estimated, also insert any commentary if the projection or target has changed and detail why] | [Insert result (against Indicator, using Measure/Unit) for baseline. Say N/A or include comment if/why gathering a baseline couldn't be gathered.] | [Insert result (against Indicator, using Measure/Unit) for Yr1] | Include any comments that are useful to interpret or understand the result. For outcomes, If you can, include an estimate of the contribution if you feel you can accurately make one base on the evidence you have collected. | [Insert result (against Indicator, using Measure/Unit) for Yr2] | [see earlier column] | [Insert result (against Indicator, using Measure/Unit) for Yr3] | [see earlier column] | [Insert any additional, relevant or important information to be aware of regarding this indicator which is not covered earlier]
INPUT | Funding | Do we/did we have the required funding in place on time and to the level agreed/approved? | The funding is in place on time and to budget | The funding is in place on time and to budget (YES/NO + commentary) | Project records |  | Annually (including part of annual reporting) | Project manager | Project records will capture this information in a format that meets our needs | n/a (use all the funding)
ACTIVITY | Design the trap | Are we developing a trap that meets both cost, usability, and acceptability (humane) design requirements? | Stakeholder(s) confirm the design will/has/is expected to meet requirements | Ask stakeholders for confirmation (Yes / No + commentary) | Project records Stakeholder survey or interview |  | Annually (including part of annual reporting) | project manager | We have a mechanism in place (e.g. A regular stakeholder workshop) where we can gather this. | All stakeholders are satisfied with the design | n/a | n/a - not relevant
SHORT-TERM OUTCOME | DOC and other pest controller buy and use the traps | To what extent are DOC and other pest control agencies (e.g. Councils or private companies) using the trap and to what extent is it meeting their needs (i.e. Easy to use, cost effective) | Intended users/customers of the trap confirm they have purchased and are using the traps | Ask stakeholder if they have purchased the trap and if they have, if they are using it (YES/NO). ALSO Ask stakeholder what feedback they have. E.g., do they find it easy to use, cost effective, are their any changes they would like to see? (QUALITATIVE/NARRATIVE) | Survey of DOC, RCs and private companies OR Stakeholder interviews |  | Six monthly? For first X years after available on the market (planned to be 1 year before end of project) | Social scientist team member | The trap is launched sufficiently in advance of the end of the project that we can run as least one or two rounds of this data collection. | N/A at the moment (see comment) | To be updated after stakeholder design workshops. Ask them to estimate how quickly this might be taken up by the market to guide our projection.
LONG-TERM OUTCOME | Improved forest ecosystem health | Is the forest ecosystem health improving following the reduction of possum numbers? | Increased number of birds | Density per square metre | mist netting |  | Bird density survey | DOC | We are able to use any annual / periodic survey that DOC or other stakeholder run. WE WON'T do this ourselves. | Unknown for now. | To be updated once the efficacy of the traps is established and stakeholders can provide some inputs on estimated uptake and use.
[As above] | [As above] |  | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above] | [As above]

## Detecting change data examples
CHANGES OR SHIFTS SOUGHT | EXAMPLES OF POSSIBLE DATA COLLECTION METHODS
Biophysical elements | Records; Diaries; Data books, trial data
Awareness of interventions | Surveying
Interviewing (phone; face-to-face)
Feedback sheets
Dart board
Focus groups
ORID reflection processes
Narratives
Diaries (book, or photo-diaries)
Team meeting discussions (collated on spreadsheets)
Records of communications
Media involvement
Records of utilisation of science
Knowledge, skill, attitude, or beliefs | Social network analysis
Team reflections
Behavioural intentions | Awards achieved
i.e. adoption, partial adoptions or adaptions | Case studies
Actual behavioural change | Citation records
i.e. adoption, partial adoption or adaptions
Engagement with different stakeholders, including next and end users of the science.
Effectiveness of intervention or event
Economic position | Cost benefit analysis
Social return on investment
Value for Money
Occurrence of events | Counts

## Secondary data - sector (hidden)
There is industry in rural areas to employ graduates. This will be a focus of the linkages and short skills training by BHI.
Graduate employment data?
Increased access to education for women
Tertiary education numbers m/f

## Context -factors (hidden)
Back to contents page
BHI - Cambodia Assumptions
Contextual factors impacting on project
Political, Social, Economic, Technological, Environmental, Other
Date | By | Comments